## tf utilization
FDP Form 6 - Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
FOR THE 2ND QUARTER, CY 2019
Province, City or Municipality: MIDSALIP
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
TF - REGULAR K CONSTRUCTION & GEN.MDSE. | BRGY.CANIPAY NORTE TO GOLICTOP FMR | 7797767.9 |  |  | 100% | 7412491.58 |  | completed
RICE PRODUCTION CENTER | TIMBABOY,MIDSALIP | 2847346.56 |  |  | 45.02% | 1281904.4 |  | completed
NATIONAL CHILD DEVELOPMENT CENTER | POB.A,MIDSALIP ZDS | 2300000 |  |  | 91.91% | 2211107.69 |  | on going
FMR CANIPAY SUR -MATALANG | BRGY.CANIPAY SUR -MATALANG | 10393393.92 |  |  | 95% | 9873986.76 |  | on going
FMR NEW KATIPUNAN-LICUROAN | BRGY.KATIPUNAN-LICUROAN | 5500000 |  |  | 50% | 1682850.28 |  | on going
FMR GUITALOS | BRGY.GUITALOS MIDSALIP ZDS | 1537771.2 |  |  | 53.49% | 631630.1 |  | on going
SJ BONIFACIO BUILDERS 1ST BILLING | BRGY. MATALANG, MIDSALIP ZDS | 5131695.3 |  |  | 49.3% | 3528050.76 |  | on going
SJ BONIFACIO BUILDERS 2ND BILLING | BRGY. MATALANG, MIDSALIP ZDS | 3253002.01 |  |  | 80.55% | 1932786.29 |  | on going
SJ BONIFACIO BUILDERS 3RD BILLING | BRGY. MATALANG, MIDSALIP ZDS | 1512283.77 |  |  | 95.08% | 1266537.66 |  | on going
SJ BONIFACIO BUILDERS 4TH BILLING | BRGY. MATALANG, MIDSALIP ZDS | 511998.57 |  |  | 100% | 428798.8 |  | completed
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
( sgd ) MARIA GLENDA D. UNABIA
LOCAL ACCOUNTANT
( sgd )LEONIDA M. ALBOR-ANGCAP
LCE, Chairman, LSB